## UTR 2009 Project Plan
No | Task | Due date | Assigned to | Status | Comments
1 | Technology Management |  | Lead: HL Halima |  | Can all items be linked?
1.01 | Create data base for student records
1.02 | Create Data base for instructor records
1.03 | Create Web page University
1.04 | Management of Email List
1.05 | Storage of New Comers Certificate material
1.06 | Calender of UTR sessions
1.07 | Create Section for Deans only - include UTR manual
2 | Heraldry |  | Lead: Mistress Alicia
2.01 | Work with Tir Righ Heralds to create Device for UTR (choice)
2.02 | Get feedback from populace on favourite device
2.03 | Determine budget to create banners for each Dean
2.04 | Work with populace on finding volunteers to create banners
2.05 | Work with Heralds on creating scroll wordings and designs for degrees
2.06 | Work with Heralds on creating scroll wording for instructor recognition
2.07 | Work with Heralds on creating recognition tokens for degree completion
2.08 | Work with Heralds on creating recognition tokens for instructors
3 | Common Forms & Dean Binders |  | Lead: Dame Elena
3.01 | Finalize common forms for Deans to use for running sessions |  | Elena |  | Forms already created; have been zipped and emailed for comment. Were submitted in 2008 to Principality Forms Deputy for fillable .pdf
3.02 | Review current forms for adequacy - do we need more or less? |  | me |  | Can revisit after Deans have commented on forms
3.03 | Determine how many binders need to be created with full information and costing | 2009-08-15 | me |  | There are 7 Deans, 3 of whom already have binders: Elena, Ysabelle, Wrenn. We would need 4 more for the current (teaching) Deans.
3.04 | Running a UTR Session |  | me
3.05 | Information Packet for Groups (Shires, Baronies) |  | Elena and Madelena?
3.06 | Deans Manual | 2009-08-30 | me |  | Run through the Yahoo email groups (2) and check for comments that were not addressed. Present updated manual to Deans, Advisors, Governor and Seneschal for comment by 30Aug09
4 | New Comers Certificate |  | Lead: Mistress Yrsa
4.01 | Analyse need for this certificate/recognition
4.02 | Review requirements
4.03 | Identify members of the populace who could create Core Material
4.04 | Co-ordinate Creation of Core Material and provide to all Deans
5 | Identify Potential events for UTR Sessions |  | Lean: HL Aine
5.01 | Review Key events in Principality for potential UTR sessions
5.02 | Create proposals for events & approach each seneschal
5.03 | Liase with Tir Righ Events Deputy to include UTR classes at Principality events
5.04. | Approach other officers about potential UTR sessions tied to their offices (IE Heralds, Marshals)
6 | Reporting |  | Lead:Dame Magdelena
6.01 | Create monthly reporting structure for Deans
6.02 | Create reporting deadlines around University Sessions
6.03 | Create Code of Conduct for Deans
6.04
6.05
6.06
6.07
7 | Other An Tir Universities |  | Lead:Dame Magdelena
7.01 | Approach the University of Avacal (THUA), Ithra and the Principality of the Summits University for cross credits |  |  |  | could be a maximum credit or for shared events - ie Crown being held in Tir Righ
7.02 | Determine agreed protocol for Avacal / Tir Righ War with THUA

## UTR Deans Binders
Item | Cost | Remarks
Binder | 18.354 | Wal-Mart, $15.96 plus taxes
Avery Ready Index 15 Tab | 0 | On Hand
Receipt Book |  | Staples, triplicate
Printing
Mailing | 15
Total Cost | 33.354